## Task Log
Task | Estimation | Completed | Notes | Issues
Research WAMP Stack | 5 | 1
Install WAMP Tools on Laptop | 1 | 1
Install WAMP Tools on Desktop | 1 | 1
Add hours to tasks | 1 | 1
Do code Review | 2 | 1
Handle php monitoring | 10 | 5 | PHP was a new language for me to learn to do this. When learning new languages I need to give these tasks higher priority
Make Use Case | 2 | 1
Make Test Case | 2 | 1
Test ReadMe and Setup Instructions | 2 | 1
Have UV of application | 4 | 2
Make readme and set up steps | 3 | 1
Make functional Requirements | 2 | 1
Make architecture diagram | 2 | 2
Adjust titles for consistency | 2 | 1
Run linter and validator on UI | 2 | 1
Make NFR Doc | 2 | 1
Implement message that keeps track of how many items are completed | 6 | 4
Make database diagram | 2 | 2
Make sequence diagram | 2 | 2
Figure out how to add contributor | 2 | 1
Make class diagram | 2 | 2
Add button implementation | 4 | 3
Implement styling | 7 | 8 | This was my biggest time sync I need to be more decisive in picking an approach
Make UI | 8 | 5
Make data flow diagram | 2 | 2
Have baseline UI posted to github | 1 | 1
Decide Delete behavior | 3 | 2
Do functional test | 3 | 3
Make burndown | 3 | 2
Make video demo | 1 | 2
Make use of wiki for docs | 5 | 2
verify correctness of docs | 3 | 2
Total | 97 | 65